## Timeline
Project Name |  | Total Duration(Days) | Start Date | End Date | Submission date
Eco-Friendly Stationery Items |  | 30 | 2021-08-26 | 2021-09-25 | 2021-09-29
Sl No. | Task Descriptions | Start Date | End Date | Duration
1 | Planning/Design
1.1 | Project Defination | 2021-08-21 | 2021-08-22 | 2
1.2 | Finish webpage | 2021-08-23 | 2021-08-24 | 2
1.3 | Project Design | 2021-08-24 | 2021-08-25 | 2
2 | Coding
2.1 | Phase 1 | 2021-08-26 | 2021-09-09 | 14
2.2 | Phase 2 | 2021-09-17 | 2021-09-21 | 4
2.3 | Additional Features | 2021-09-22 | 2021-09-24 | 3
3 | Testing
3.1 | Phase 1 Testing | 2021-08-26 | 2021-09-09 | 14
3.2 | Modification /Any changes | 2021-09-04 | 2021-09-09 | 6
3.3 | Phase 2 Testing | 2021-09-16 | 2021-09-21 | 5
3.4 | Modification /Any changes | 2021-09-21 | 2021-09-24 | 4
3.5 | Final Testing | 2021-09-21 | 2021-09-24 | 4
4 | Documentation
4.1 | User Guide | 2021-09-19 | 2021-09-24 | 6
4.2 | Presentation | 2021-09-22 | 2021-09-24 | 3

## Roles & Responsiblity
Roles And Responsiblities
1 | Role | Team Leader,User UI
| Member Name | Amrita Sutar
| PRN No | 210543181007
| Description | Managed Team & all work, designed front end part of user module
2 | Role | Database, Hibernate
| Member Name | Bhushan Chaudhari
| PRN No | 210543181015
| Description | Designed database tables & implemented hibernate back end part
3 | Role | Back End
| Member Name | Rohan Patil
| PRN No | 210543181063
| Description | Designed back end part of spring boot application & all api mappings
4 | Role | Admin UI, Documentation
| Member Name | Shubham Patil
| PRN No | 210543181065
| Description | Designed front end part of layout pages, admin module & all documentation work